## Gantt Chart w % Complete
ECSE 395 — Memorial Bird Feeder Gantt Chart
Course dates: supplied Canvas assignment list, Fall 2026. FS/TS due Sep 14 and brainstorming due Sep 21 are prior work, not future tasks. | [20 empty] | Plan end date | 2026-12-09
DRAFT execution tasks and team milestones. Course deadlines confirmed from attachment. Confirm owners, selected concept and actual progress.
September 28–December 9, 2026. Blue = scheduled week; M = milestone. Days available counts calendar days, including both endpoints and weekends. A same-day window is 1 day.
ID | Subsystem task | Start date | Type | End date | Days available | Predecessor IDs | Related specs | Responsible person(s) | Complete | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Notes / due time | Canvas assignment source
[10 empty] | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07
Concept selection and architecture
R1 | Finalize concept choice and Gantt submission | 2026-09-28 | 28 | 2026-09-28 | 1 | 0 | 0 | Ayan, Daniel, Emmett, Joseph | [12 empty] | Same-day course deadline. Confirm actual submission status. Earlier specifications and brainstorming are prior work. | bar: 2026-09-28
R2 | Define subsystem interfaces and prototype questions | 2026-09-29 | 29 | 2026-10-01 | 3 | 0 | 2 | Ayan, Daniel, Emmett, Joseph | bar: 2026-09-28
R3 | Write architecture and three-prototype plan | 2026-10-02 | 2 | 2026-10-05 | 4 | 0 | 3 | Ayan, Daniel, Emmett, Joseph | [12 empty] | Prototype 1/2/3 mapping below is proposed, pending the selected concept and assignment brief. | bar: 2026-09-28 to 2026-10-05
R4 | Define measurable verification and validation methods | 2026-10-06 | 6 | 2026-10-09 | 4 | 0 | 3 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-05
R5 | Review and submit verification and validation plan | 2026-10-12 | 12 | 2026-10-12 | 1 | 0 | 0 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-12
Seed protection and bird access — proposed Prototype 1
S1 | Design seed-loss mechanism and bird clearances | 2026-09-29 | 29 | 2026-10-02 | 4 | 0 | 3 | Ayan, Daniel, Emmett, Joseph | bar: 2026-09-28
S2 | Source stock materials and build quick mockup | 2026-10-05 | 5 | 2026-10-07 | 3 | 0 | 2 | Daniel | [12 empty] | Use available materials for the early prototype. Order long-lead MVP parts by Oct 2. | bar: 2026-10-05
S3 | Test mockup and capture evidence for check-in | 2026-10-08 | 8 | 2026-10-08 | 1 | 0 | 0 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-05
S4 | Refine seed protection using prototype findings | 2026-10-12 | 12 | 2026-10-16 | 5 | 0 | 4 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-12
Rain protection and drainage — proposed Prototype 2
W1 | Design rain coverage and drainage paths | 2026-09-29 | 29 | 2026-10-02 | 4 | 0 | 3 | Ayan, Daniel, Emmett, Joseph | bar: 2026-09-28
W2 | Build quick weather and drainage mockup | 2026-10-05 | 5 | 2026-10-07 | 3 | 0 | 2 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-05
W3 | Run water tests and record check-in evidence | 2026-10-08 | 8 | 2026-10-08 | 1 | 0 | 0 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-05
W4 | Refine rain protection and drainage | 2026-10-12 | 12 | 2026-10-16 | 5 | 0 | 4 | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-12
Mounting and refill access — proposed Prototype 3
A1 | Measure feeder, inscription and window access | 2026-09-29 | Task | 2026-10-02 | 4 | R1 | FS.04–FS.06 | Ayan | bar: 2026-09-28
A2 | Design removable mounting and service access | 2026-10-05 | 5 | 2026-10-09 | 5 | 0 | 4 | Daniel | bar: 2026-10-05
A3 | Build mount and rehearse refill/cleaning tasks | 2026-10-12 | 12 | 2026-10-14 | 3 | 0 | 2 | Emmett | bar: 2026-10-12
A4 | Check visibility, damage and refill clearance | 2026-10-15 | 15 | 2026-10-15 | 1 | 0 | 0 | Joseph | [12 empty] | Preserve inscription and original feeder. Automatic or remote refilling remains outside scope. | bar: 2026-10-12
Controls and power — conditional on selected concept
E1 | Define sensing, control states and power needs | 2026-09-29 | Conditional | 2026-10-02 | 4 | R1 | Selected concept TS | Ayan, Daniel, Emmett, Joseph | [12 empty] | Remove these tasks if the selected concept is passive. | bar: 2026-09-28
E2 | Order parts and develop controller logic | 2026-10-05 | Conditional | 2026-10-09 | 5 | E1 | Selected concept TS | Daniel | bar: 2026-10-05
E3 | Assemble and bench-test controls and power | 2026-10-12 | Conditional | 2026-10-16 | 5 | E2 | Selected concept TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-12
E4 | Integrate enclosure, wiring and service mode | 2026-10-19 | Conditional | 2026-10-23 | 5 | E3 | Selected concept TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-19
Prototype reviews, midterm and MVP integration
P1 | Order MVP materials and track deliveries | 2026-09-29 | Task | 2026-10-16 | 18 | R1 | All subsystems | Daniel | [12 empty] | Resolve lead times early enough for Oct 19 integration. | bar: 2026-09-28 to 2026-10-12
M1 | Team milestone: Prototypes 1 and 2 ready | 2026-10-08 | Team milestone | 2026-10-08 | 1 | S3, W3 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-05
M2 | Team milestone: Prototype 3 ready | 2026-10-15 | Team milestone | 2026-10-15 | 1 | A4 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-12
P2 | Prepare midterm slides and individual speaking parts | 2026-10-16 | Task | 2026-10-20 | 5 | M2 | All FS / TS | Ayan and Joseph | [12 empty] | Include all three prototype findings and concept rationale. | bar: 2026-10-12 to 2026-10-19
P3 | Package prototype evidence and rehearse midterm | 2026-10-19 | Task | 2026-10-20 | 2 | S4, W4, A4 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-19
M3 | Team milestone: midterm package ready | 2026-10-20 | Team milestone | 2026-10-20 | 1 | P2, P3 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-19
I1 | Assemble MVP mechanical interfaces | 2026-10-19 | Task | 2026-10-23 | 5 | S4, W4, A4, P1 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-19
I2 | Test MVP operation and correct integration faults | 2026-10-26 | Task | 2026-10-27 | 2 | I1; E4 if used | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-26
M4 | Team milestone: MVP ready for submission | 2026-10-27 | Team milestone | 2026-10-27 | 1 | I2 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-26
I3 | Capture MVP evidence and prepare progress check-in | 2026-10-28 | Task | 2026-10-29 | 2 | M4 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-26
Verification, validation and data analysis
V1 | Verify seed loss, access and rain performance | 2026-10-29 | Task | 2026-11-05 | 8 | M4, R5 | FS.01–FS.03 / linked TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-10-26 to 2026-11-02
V2 | Validate refill, inscription and upkeep with stakeholder | 2026-10-29 | Task | 2026-11-05 | 8 | M4, R5 | FS.04–FS.06 / linked TS | Joseph | [12 empty] | Arrange stakeholder availability beforehand. Record task success, service effort and feedback. | bar: 2026-10-26 to 2026-11-02
V3 | Arrange stakeholder testing appointment | 2026-10-19 | Task | 2026-10-23 | 5 | R5 | FS.04–FS.06 | Joseph | bar: 2026-10-19
V4 | Complete test evidence and validation checkpoint | 2026-11-06 | Task | 2026-11-09 | 4 | V1, V2 | All linked TS | Ayan | bar: 2026-11-02 to 2026-11-09
M5 | Team milestone: first test dataset complete | 2026-11-05 | Team milestone | 2026-11-05 | 1 | V1, V2 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-02
V5 | Analyze results against targets and document failures | 2026-11-10 | Task | 2026-11-12 | 3 | V4 | All linked TS | Joseph | bar: 2026-11-09
V6 | Finalize data analysis and improvement priorities | 2026-11-13 | Task | 2026-11-16 | 4 | V5 | All linked TS | Ayan | bar: 2026-11-09 to 2026-11-16
V7 | Implement priority fixes and repeat affected tests | 2026-11-17 | Task | 2026-11-23 | 7 | V6 | Failed TS criteria | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-16 to 2026-11-23
M6 | Team milestone: design and test evidence frozen | 2026-11-23 | Team milestone | 2026-11-23 | 1 | V7 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-23
Stakeholder preparation, final report and presentations
D1 | Prepare stakeholder MVP presentation materials | 2026-11-17 | Task | 2026-11-19 | 3 | V6 | All FS / TS | Joseph | [12 empty] | Actual stakeholder presentation date was not listed in the supplied Canvas view. | bar: 2026-11-16
D2 | Draft group report and requirement traceability | 2026-11-16 | Task | 2026-11-25 | 10 | V5 | All FS / TS | Emmett | [12 empty] | Incorporate analysis Nov 16 and retest evidence Nov 23 as they become available. | bar: 2026-11-16 to 2026-11-23
D3 | Draft individual reports and contributions | 2026-11-23 | Task | 2026-11-25 | 3 | V6 | Individual deliverable | Emmett | bar: 2026-11-23
D4 | Review group/individual reports and final evidence | 2026-11-30 | Task | 2026-12-02 | 3 | M6, D2, D3 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-30
D5 | Finish reports, CATME and Week 14 log | 2026-12-03 | Task | 2026-12-04 | 2 | D4 | Course deliverables | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-30
M7 | Team milestone: reports ready to submit | 2026-12-03 | Team milestone | 2026-12-03 | 1 | D4 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-11-30
D6 | Build final slides and demonstration sequence | 2026-11-30 | Task | 2026-12-04 | 5 | M6 | All FS / TS | Joseph | bar: 2026-11-30
D7 | Rehearse group and individual presentation parts | 2026-12-07 | Task | 2026-12-08 | 2 | D6 | Course deliverables | Ayan, Daniel, Emmett, Joseph | bar: 2026-12-07
M8 | Team milestone: final presentation ready | 2026-12-08 | Team milestone | 2026-12-08 | 1 | D7 | All FS / TS | Ayan, Daniel, Emmett, Joseph | bar: 2026-12-07
D8 | Final presentation delivery / submission | 2026-12-09 | Task | 2026-12-09 | 1 | M8 | Course deliverables | Josp | [12 empty] | Canvas lists 11:59 PM due time. Confirm the actual in-class presentation slot. | bar: 2026-12-07
Weekly project logs — preparation
L6 | Maintain and submit Week 6 project log | 2026-09-28 | Task | 2026-10-02 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-09-28
L7 | Maintain and submit Week 7 project log | 2026-10-05 | Task | 2026-10-09 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-10-05
L8 | Maintain and submit Week 8 project log | 2026-10-12 | Task | 2026-10-16 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-10-12
L9 | Maintain and submit Week 9 project log | 2026-10-19 | Task | 2026-10-23 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-10-19
L10 | Maintain and submit Week 10 project log | 2026-10-26 | Task | 2026-10-30 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-10-26
L11 | Maintain and submit Week 11 project log | 2026-11-02 | Task | 2026-11-06 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-11-02
L12 | Maintain and submit Week 12 project log | 2026-11-09 | Task | 2026-11-13 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-11-09
L13 | Maintain and submit Week 13 project log | 2026-11-16 | Task | 2026-11-20 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-11-16
L14 | Maintain and submit Week 14 project log | 2026-11-30 | Task | 2026-12-04 | 5 |  | Course log | Ayan, Daniel, Emmett, Joseph | [12 empty] | Collect contributions during the week. Canvas submission due 11:59 PM on end date. | bar: 2026-11-30
Course milestones — confirmed from supplied Canvas attachment
C1 | Concept Selection & Gantt Chart | 2026-09-28 | Course milestone | 2026-09-28 | 1 | R1 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757766 | bar: 2026-09-28
C2 | Week 6 project log | 2026-10-02 | Course milestone | 2026-10-02 | 1 | L6 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757794 | bar: 2026-09-28
C3 | System Architecture and Prototype Plan | 2026-10-05 | Course milestone | 2026-10-05 | 1 | R3 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757809 | bar: 2026-10-05
C4 | Week 7 Team Progress Check-in: Prototypes 1 and 2 | 2026-10-09 | Course milestone | 2026-10-09 | 1 | M1 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780841 | bar: 2026-10-05
C5 | Week 7 project log | 2026-10-09 | Course milestone | 2026-10-09 | 1 | L7 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757795 | bar: 2026-10-05
C6 | Verification and Validation Plan | 2026-10-12 | Course milestone | 2026-10-12 | 1 | R5 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757811 | bar: 2026-10-12
C7 | Week 8 Team Progress Check-in: Prototype 3 | 2026-10-16 | Course milestone | 2026-10-16 | 1 | M2 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780842 | bar: 2026-10-12
C8 | Week 8 project log | 2026-10-16 | Course milestone | 2026-10-16 | 1 | L8 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757796 | bar: 2026-10-12
C9 | Midterm Group Presentation | 2026-10-21 | Course milestone | 2026-10-21 | 1 | M3 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757799 | bar: 2026-10-19
C10 | Midterm Individual Presentation Grade | 2026-10-21 | Course milestone | 2026-10-21 | 1 | M3 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 3:00 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757800 | bar: 2026-10-19
C11 | Prototypes 1, 2, and 3 | 2026-10-21 | Course milestone | 2026-10-21 | 1 | P3 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/771306 | bar: 2026-10-19
C12 | Week 9 project log | 2026-10-23 | Course milestone | 2026-10-23 | 1 | L9 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757797 | bar: 2026-10-19
C13 | MVP (Minimally Viable Prototype) | 2026-10-28 | Course milestone | 2026-10-28 | 1 | M4 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757798 | bar: 2026-10-26
C14 | Week 10 Team Progress Check-in: MVP | 2026-10-30 | Course milestone | 2026-10-30 | 1 | I3 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780843 | bar: 2026-10-26
C15 | Week 10 project log | 2026-10-30 | Course milestone | 2026-10-30 | 1 | L10 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757785 | bar: 2026-10-26
C16 | Week 11 Team Progress Check-in: Verification + Validation Testing | 2026-11-06 | Course milestone | 2026-11-06 | 1 | M5 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780844 | bar: 2026-11-02
C17 | Week 11 project log | 2026-11-06 | Course milestone | 2026-11-06 | 1 | L11 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757786 | bar: 2026-11-02
C18 | Validation Testing Checkpoint | 2026-11-09 | Course milestone | 2026-11-09 | 1 | V4 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757808 | bar: 2026-11-09
C19 | Week 12 Team Progress Check-in: Data Analysis | 2026-11-13 | Course milestone | 2026-11-13 | 1 | V5 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780845 | bar: 2026-11-09
C20 | Week 12 project log | 2026-11-13 | Course milestone | 2026-11-13 | 1 | L12 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757787 | bar: 2026-11-09
C21 | Data Analysis Checkpoint | 2026-11-16 | Course milestone | 2026-11-16 | 1 | V6 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757768 | bar: 2026-11-16
C22 | Week 13 Team Progress Check-in: Stakeholder MVP Presentation Preparations | 2026-11-20 | Course milestone | 2026-11-20 | 1 | D1 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 2:05 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/780846 | bar: 2026-11-16
C23 | Week 13 project log | 2026-11-20 | Course milestone | 2026-11-20 | 1 | L13 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757788 | bar: 2026-11-16
C24 | Extra Credit Opportunity: End-of-Semester Course Evaluation | 2026-12-04 | Course milestone | 2026-12-04 | 1 |  | Course milestone | Optional | [12 empty] | Due 11:59 PM, as displayed in Canvas. Optional extra credit. | https://canvas.case.edu/courses/54050/assignments/757770 | bar: 2026-11-30
C25 | Final report | 2026-12-04 | Course milestone | 2026-12-04 | 1 | M7 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757776 | bar: 2026-11-30
C26 | CATME Peer Evaluation | 2026-12-04 | Course milestone | 2026-12-04 | 1 | D5 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757763 | bar: 2026-11-30
C27 | Final report (individual) | 2026-12-04 | Course milestone | 2026-12-04 | 1 | M7 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757777 | bar: 2026-11-30
C28 | Week 14 project log | 2026-12-04 | Course milestone | 2026-12-04 | 1 | L14 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757789 | bar: 2026-11-30
C29 | Final presentation (group) | 2026-12-09 | Course milestone | 2026-12-09 | 1 | M8 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757774 | bar: 2026-12-07
C30 | Final presentation (individual) | 2026-12-09 | Course milestone | 2026-12-09 | 1 | M8 | Course milestone | Ayan, Daniel, Emmett, Joseph | [12 empty] | Due 11:59 PM, as displayed in Canvas. | https://canvas.case.edu/courses/54050/assignments/757775 | bar: 2026-12-07
Revision history
Revision | Description | Date | Updated by
1 | Added team member assignments and revision-history table | 2026-10-12T00:00:00.000Z | Daniel Lim